## Slide 1
江貫榮 研究助理
Notes: 大家好，我們是子計畫二。

## Slide 2
工作內容
計畫名稱 | 工作內容 | 時程 |  |  |  |  |  | 
 |  |  | 第三季 |  |  | 第四季 |  | 
 |  | 6月 | 7月 | 8月 | 9月 | 10月 | 11月 | 12月
子計畫二 感測資料收集通訊程式設計與實作 | 1.設計感測資料收集通訊系統之架構 |  |  |  |  |  |  | 
 | 2.實作感測資料收集系統之閘道器端 |  |  |  |  |  |  | 
 | 3.模擬感測資料之傳輸通訊過程 |  |  |  |  |  |  | 
 | 4.規範感測資料傳輸之格式 |  |  |  |  |  |  | 
 | 5.實際驗證通訊系統之可行性 |  |  |  |  |  |  | 
Notes: 這是我們的工作內容安排。

## Slide 3
經費使用
子計畫名稱 |  | 經費使用 |  |  |  |  |  | 
 |  | 第二季 | 第三季 |  |  | 第四季 |  | 
 |  | 6月 | 7月 | 8月 | 9月 | 10月 | 11月 | 12月
子計畫二：(王勝德) 感測資料收集通訊程式設計與實作 | 使用經費 | 人力費:43288 耗材費:23165 設備費:0 會議費:0 管理費:0 | 人力費:43288 耗材費:22082 設備費:88728 會議費:0 管理費:0 | 人力費:43288 耗材費:40000 設備費:0 會議費:0 管理費:0 | 人力費:98884 耗材費:31586 設備費:0 會議費:0 管理費:0 | 人力費:98884 耗材費:8641 設備費:0 會議費:0 管理費:0 |  | 
 | 累計使用經費百分比 | 3.37% | 11.19% | 15.41% | 22.03% | 27.49% |  | 
Notes: 這是我們的經費使用狀況。

## Slide 4: Outline
Review of Intelligent Gateway
Implementation Problem of BLE Agent
C language
Notes: 這邊列出的是這次報告的大綱。

## Slide 5: Review - Architecture
使用者端
Intelligent
Gateway
Sensor
雲端
國網中心
子計畫二
其他子計畫
&
科技部單位
Notes: 現在回顧一下我們的架構。（解釋）

## Slide 6: Review - Intelligent Gateway
MQTT Broker
mosquitto
BLE Agent
(Python)
Auth Identity
Center
(Python)
Data
Center
(Python)
UE
Sensor A
BLE
Subscribe
Service:
DL Service
UL Service
Characteristics:
DL Char
UL Char
BLE
Gateway (Ubuntu Linux on Shuttle)
Service:
DL Service
UL Service
Characteristics:
DL Char
UL Char
Publish
Notes: 我們看其中的Intelligent Gateway，最重要的三個組成部分就是BLE Agent、安全認證中心和Data Center

## Slide 7: Review - Multi BLE module
Socket communication
New device!
BLE Agent
(Python)
BLE Scanner
(Python)
New user/ new device
Scan…
Find new device!
Send MAC to BLE Agent
Connect
Notes: 這是自動找到新的device的實作方法，上次講解過這次不再細講。

## Slide 8: Implementation Problem of BLE Agent
Problem Description
  Connection Error
  Library: pygatt (on GitHub)
    Fuction: write_by_handle()
Conducted Test
  Different Hardware
  Different Location
Possible Reason
  Bug of pygatt
  Newer hardware needed
  Signal Interferenc
Notes: 但是我們在實作BLE Agent時遇到了一些困難。下面分成問題描述、之前做過的測試、問題可能的原因、以及接下來的嘗試方向，這四個方面來討論。

## Slide 9: Gatttool in Bluez
Bluez
  Officical Linux Bluetooth protocol stack
Gatttool
  One executable tool in Bluez package
  Written in C
  Allowing user to control BLE device in terminal
  No downlink error in our tests

## Slide 10: BLE agent in C
BLE agent in Python
Advantage:
Easier to program
Disadvanage:
Slower
Bug of Pygattlib
Fewer function
BLE agent in C
Advantage:
Faster
Stable
More general
Disadvanage:
Harder to program

## Slide 11: Progress
Modified gatttool
From one connections to two connections
Able to receive packets from sensors
Downlink without error

## Slide 12: 報告結束
感謝您的聆聽
問題與討論